## Sheet1
Date | Task | Time (h) | Running Total (h) | Target (h) | On Target?
2025-02-10 | Reading | 1 | 1 |  | _
2025-02-14 | Reading and exploring tools like Kaggle | 2 | 3 |  | _
2025-02-18 | Exploring and brainstorming project ideas | 3 | 6 | 5 | 1
| Gathering and preliminarily evaluating datasets | 2 | 8 |  | _
| Restricting project ideas and reaching out for additional information | 1 | 9 |  | _
2025-02-22 | Running quick 'proof of concept' tests on datasets | 2 | 11 |  | _
| Comparing potential projects pros, cons and limitations | 2 | 13 |  | _
2025-02-26 | Fully exploring / crystallizing project boundaries, settling on a concept | 1 | 14 | 15 | -1
| Submitting initial proposal | 0.5 | 14.5 |  | _
2025-02-28 | Planning | 2 | 16.5 |  | _
| Writing TN1 | 4 | 20.5 |  | _
2025-03-01 | Finalize and submit TN1 | 2 | 22.5 | 20 | 2.5
| Exploration on NLP and sentiment analysis | 1 | 23.5